## In Development
AB 109 Contracts in Development
Item | Description/Summary | AB 109 Allocation | Status
Employment Vendor Pool | Employment Services | 3000000 | Round 5: One bid was received and is under evaluation.
Housing: Genesis Worship Center - Fresh Start Academy | 12 Housing Units |  | Finalizing contract details
AC Reentry Housing Vendor Pool | The Housing Vendor Pool will help establish immediate assistance to participants who are homeless or at risk of homelessness. Services available include: housing case management, emergency shelter, transitional housing, assistance securing long-term housing and short-term rental assistance, if needed. Flexibility allows responsiveness to the needs of participants. | TBD | RFPQ is in development
Female & Male Residential Multi-Service Center | Residential Program that will have wrap-around services on site and help transition individuals from incarceration, to stability to community. | 2000000 | The RFP is being drafted with GSA.
Education (New Bid) | Provides high school diploma, GED, or HiSet. Career training, English as a second languge, and other academmic support and resources, as well as, transitional services and college tuition assistance. | TBD | The current contract expires 12/31/21. The SOW was submitted to GSA on 9/28/20. GSA anticipates releasing the RFP in early 2021.
Family Reunification: Legal & Therapy Services (Re-Bid) | Therapy & Legal Services in Support of Family Reunification Programs are evidence-based programs that work with current and formerly incarcerated individuals to promote successful reunification with family members and/or support systems. | 1000000 | The SOW was submitted to GSA in November; GSA is drafting the RFP.
Sex Offender Treatment | Required sex offender treatment | 550000 | The SOW was submitted to GSA in September; GSA is drafting the RFP. GSA intends to release the RFP in December.
Cognitive Behavior Intervention Services & Incentives | • For all Probation supervised clients • To be provided to all individuals supervised by Probation to ensure better programming outcomes by addressing criminal thinking. | 500000 | The RFP is routing for final approval through management. The RFP will post upon management approval.
Client Resource Forums | • Establish CBO-operated Client Resource Forums county-wide • This would fund a CBO who will run meetings within the community for clients to receive information about services, connect with one another, and connect with other providers. | 250000 | The SOW is being revised due to COVID. The SOW will be submitted to GSA in November.
Leadership & Entrepreneurship | • Funding for smaller organizations owned and operated by formerly incarcerated to ensure that when additional funding is released, the RFP targets the formerly incarcerated who own and/or operate businesses. | 1000000 | The SOW was submitted to GSA on 10/28/20, GSA is drafting an RFP.
Faith-Based/Local Community Partnerships | • Include Faith Partners in effort to support clients • This line item is intended to acknowledge and provide support to those smaller organizations that are already doing the work, not for organizations to start a service. • Unresolved issues: There are many small church organizations that do the work but do not have the infrastructure necessary to perform on a county contract nor negotiate the County procurement process. | 1000000 | A listening session was held in May. The SOW is being developed.
Women/Mother’s Services | • Dr. Barbara Bloom (toolkit attached) and Kim Carter with a Time for Change model for women’s services. | 1000000 | A listening session is being scheduled for early 2021, the SOW is being researched.
Transition Aged Youth Services/Support | • A CBO to serve as a subject-matter expert on TAY (18-25) services between the adult and juvenile service system; • CBOs and governmental partners need help with the youth-to-adult transition, along with communication between all parties. | 1000000 | A listening session is being scheduled for early 2021, the SOW is being researched.
Kinship Reentry Workforce | Program in development | 250000 | The SOW has been drafted and is routing internally, the SOW will be submitted to GSA upon management approval.
Evidenced-Based Practices Capacity Building Workshops | • Capacity building for smaller organizations (similar to the CCF) who are working with the reentry population but have never received County funding or very little, under $100,000. | 500000 | SOW needs to be researched
LGBTQ Transgender Resources | • Develop list of resources for the LGBTQ community | 100000 | SOW needs to be researched
Restorative Justice Circles for Adults | • Circles of Support & Accountability (Fresno Pacific University’s Center for Peacemaking – COSA program) • Have Circles (modeled after San Quentin Circles) • Issue to be resolved: Is this pre-conviction as well as post- conviction? Are these circles or restorative justice models that include the victim and perhaps victim restitution? | 1000000 | SOW needs to be researched
Father Services | • Programs with child-friendly services that supports single fathers, including and beyond treatment • This item will provide services that address the needs of custodial parents that are fathers and will address the lack of services for parenting fathers. | 250000 | SOW research being conducted.
Indigent/Barrier Removal Fund | • Assistance with cell phone bills to keep clients connected • Assistance to pay for post office boxes or physical addresses for clients who are homeless • Prescription/medical coverage (until Medi-Cal is obtained), birth certificate, social security card, return to work documents, Driver’s License, etc. • Funds available for childcare/preschool & afterschool care • Funds to support housing needs • Pay for technology (internet) • This funding is intended for short-term/immediate needs as individuals are applying and/or waiting for long-term services. This fund will help stabilize individuals until they are able to get connected to more permanent services. The funds will need to be capped on a dollars/person basis. Individuals must be engaged in services to be eligible for the funds. • To be determined: Development of very specific guidelines for what the funds could be used for, accounting of the funds, what happens if any part goes unused, and limits per client. | 2000000 | on-hold
Clinics for Reentry Legal Barrier Removal | • Ensure that people understand what those barriers are and increase self-advocacy tools. | 250000 | SOW needs to be researched
Reentry Client Access Communication and Service Portal | • The portal will be used to develop an interactive client application used by clients to access services, reach Deputy Probation Officers, and more. | 300000 | SOW needs to be researched
Opioid and Alcohol Use Prevention Programs | Program under review | 500000 | SOW needs to be researched
Prison Pre-Release Planning and Case Management | • Better pre-release planning with transportation planning; provide essential services for first 72 hours post-release; warm hand-offs (not in name only but in practice) to help those with small things like taking the bus, how to use the phone, etc.; include peer-mentoring for those leaving prison; system to track release processes to be better able to anticipate and plan for release. | 1000000 | SOW needs to be researched